## Overarching Goal #1
Objective (SMART) Specific, Measurable, Achievable, Realistic, Time | Actions | Responsibility (Who will do it?) | Performance Indicators/Outcomes (How will achievement(s) be measured?) | Resources Required | Target Date | Status (Frequency to be evaluated)
Overarching Goal# 1 Establish a culture of wellness by building an infrastructure that values life balance and advances the spiritual, social, emotional, financial, intellectual, occupational, environmental, and physical dimensions of wellness.
Establish the Pace University Office of Wellness | Develop proposal for a Pace University Wellness Office to be led by a full-time Chief Wellness Officer (CWO); CWO will report directly to President | Chief Wellness Officer to discuss intended plans, budget, and reporting with the Provost and President | Appointment of full-time Chief Wellness Officer and appropriate staffing for the Wellness Office; office fully operational by the end of year one | Fall 2022 budget submission for FY 24 start, to include staffing (full-time CWO, full-time staff support, part-time webmaster/social media expert) and designated office space/s | July, 2023 | Every 3 months
Expand networks of wellness-focused support services, resources, and programs for the Pace community | Examples: Protocall; Radical Health; Born this Way; Healthy Minds Survey; green spaces; conservation measures; affiliate groups; financial literacy and planning; career development; mentorship; spiritual support; weekly wellness day activities; annual wellness day | Student Success; Psychological Counseling, Chief Wellness Officer; Human Resources; faculty leadership; University Administration | Participation; satisfaction; retention | Funding for Protocall (annual) and Active Minds Survey (every 2-3 years), green space enhancement; staff to support programs; program funding, as appropriate; spiritual counselors; additional Psychological Counseling staff | August, 2023 | Following each program and initiaitve; annual overall review
Establish a holistic Health and Wellness Center to support and educate the Pace community. | 1) Revisit the idea of housing all health and wellness centers at each Pace campus under centralized leadership; 2) Assess current wellness/ meditation room existence and usage on each campus; 3) Establish sites for wellness centers to include resources such as sleep pods, healthy snacks, Zen gardens, labyrinths, and educational materials (examples of existing wellness centers: https://www.csun.edu/src and https://www.csun.edu/oasis). | Chief Wellness Officer in collaboration with: (1) Dyson College Institute for Sustainability and the Environment; (2) Development & Alumni Relations; (3) Facilities Management; (4) Wellness Advisory Committee; and the (5) VP for Student Affairs and associate deans for students | Space utilization; focus group feedback; point of service e-surveys; satisfaction ratings on Great Colleges to Work for survey, Campus Climate survey, NSSE survey | Designated spaces on each campus, equipment, annual budget for equipment acquisition and maintenance, staff/student volunteers | December, 2024 | Semi-annually
Partner with HR, faculty leadership, and the Center for Student Engagement to address work-life and school-life balance | 1) Meet with stakeholders; 2) Review literature review to identify factors that influence work-life and school-life balance; 3) Implement potential solutions. | Chief Wellness Officer and Wellness Advisory Committee; Human Resources; Joint Faculty Council officers; VP of Student Affairs and associate deans for students | Buy-in from all partners/stakeholders; improved satisfaction ratings on Great Colleges to Work for survey, Campus Climate survey, NSSE survey | Program funding; staff support | July, 2023 | Semi-annually
Address availability of spiritual support at Pace University with an eye toward ensuring the presence of spiritual advisors. | Assess current status of spiritual advisors at Pace; identify strategies for increasing the presence of spiritual advisors. | Spiritual dimension team of fhe Wellness Advisory Committee; Chief Wellness Officer | Volunteer or paid spiritual advisor/s in place to provide support for students, faculty, and staff all Pace campuses. | Budget for spiritual advisor (if volunteer support is not available) | January, 2023 | Annually

## Overarching Goal #2
Objective (SMART) Specific, Measurable, Achievable, Realistic, Time | Actions | Responsibility (Who will do it?) | Performance Indicators/Outcomes (How will achievement(s) be measured?) | Resources Required | Target Date | Status (Frequency to be evaluated)
Overarching Goal #2: Prioritize wellness across Pace University by connecting students, faculty and staff to resources and opportunities that enhance wellbeing.
The University will commit to being a health-promoting institution. | Broadly communicate the Wellness Strategic Plan within the Pace Community; consider signing on as an Okanagan Charter consortium member | CWO; student engagement; Psych Counseling; University Relations (Wellness Strategic Plan roll out) | Wellness Strategic Plan "town hall" meetings are held 3-4 times for feedback; Wellness Charter is established and communicated to all stakeholders | Staff time to support town hall meetings and finalize the Wellness Strategic Plan; staff to represent Pace as a wellness consortium member | December, 2022 | Annually
Offer at least 8 web-based University-wide wellness programs annually based on the dimensions of wellness | Identify topics; identify speakers; advertise programs; promote community attendance, participation, and evaluation; offer programs | Wellness Advisory Committee teams to recommend program topics to CWO; CWO and staff organize programming in collaboration with College of Health Professions communications team | Participation, perceived/actual impact (surveys to be analyzed for each offering); use of self-assessments, # completing certificates and badges | Budget for any external speakers; IT support; College of Health Professions communication team support | Monthly - during fall/spring semesters | End of each program
Offer at least 2 in-person campus-based wellness programs annually focusing on one or more wellness dimensions | Identify topics; identify speakers; advertise programs; promote community attendance and participation | Wellness Advisory Committee teams to recommend program topics to CWO; CWO organizes programming in collaboration with College of Health Professions communications team | Participation, perceived/actual impact (surveys to be analyzed for each offering); use of self-assessments, # completing certificates and badges | Budget for any external speakers; IT support; CHP will handle program promotion, including social media | once each semester (fall & spring) | End of program surveys to be analyzed for each offering.
Offer at least 2 mini-grants to students and employees to develop wellness initiatives | Send out call for proposals; select 2 qualified applicants to receive grant funding | Wellness Advisory Committee teams to recommend program topics to CWO; CWO organizes programming in collaboration with College of Health Professions communications team | Evaluation plan, goals and outcome measures submitted by grant recipients for approved by CWO for funding | Up to $2500 per grant recipient in year 1, to progressively increase based on budget availability | Proposals due annually in October for spring implementation | Assessment report due June 1st, annually

## Overarching Goal #3
Objective (SMART) Specific, Measurable, Achievable, Realistic, Time | Actions | Responsibility (Who will do it?) | Performance Indicators/Outcomes (How will achievement(s) be measured?) | Resources Required | Target Date | Status (Frequency to be evaluated)
Goal #3: Increase awareness, access to, and participation in programs and other initiatives that support wellness journeys.
Offer certificates and badges to Pace community (e.g. Resilience Badge, Wellness Certificate) | Identify existing programs that are compatible with badges or certificates; collaborate with PESP to create new badges/certificates | Chief Wellness Officer and Vice President, Professional Education, Interdisciplinary, and Special Programs (PESP); Wellness Advisory Committee | Awarding of badges/certificates (total number TBD) | Staff (IT, PESP) | January, 2023 | Upon completion of each program
Enhance access to mental health support resources for students by monitoring the use and effectiveness of 24/7 ProtoCall service | Implement contract with ProtoCall | ProtoCall staff, Psychological Counseling, Residential Life | Use of ProtoCall service; indicators established by Protocall, e.g., student response to availability, accessibility and usefulness of the service | Annual contract; follow up by University Psychological Counseling; marketing to communicate availability of this resource | Protocall to start Fall 2022 | Monthly usage review; semi-annual data review with respect to established parameters of effectiveness
Promote Pace’s wellness vision by improving nutrition content, appeal and affordability of food offerings in cafeterias, kiosks, and vending machines | Identify locations and offerings on PLV, NYC, WP, Valhalla campuses; assess current status through focus groups and/or student/employee surveys that review current offerings in cafeterias, kiosks, and vending machines; investigate alternate healthy offerings. | Auxiliary Services (Finance & Administration) – to review/ negotiate contracts with vendors, in consultation with CWO and Pouring Rights Committee. | Sales data to assess purchase of healthier options compared to prior offerings (data tracking for 1 yr to allow acclimation to new vendor offerings) | University Relations staff (for Health & Wellness Marketing Campaign and communication about why Pace is undertaking this initiative) | June, 2023 | every 6 months
Establish resources to support health and deliver nutrition messaging for the Pace community. | (1) Expand educational opportunities and information in the cafeteria and around campus to promote healthy eating – e.g., fruit or vegetable of the week, recipe ideas, etc.; (2) employ Dietitian/Health Coach as resource for educational events and individual/group counseling; (3) ensure student meal plans are affordable and sufficient to meet their nutritional needs; (4) eenchmark with other institutions who promote wellness – compare NYC cafeteria with PLV | Chartwell’s - in conjunction with CHP; Aux Services (Finance & Admin) – to review/negotiate contracts with Chartwells | (1) Sales data from cafeteria to assess sales of healthier options compared to prior offerings; (2) pre & post focus groups with students to assess healthy food preferences, affordability, suggestions for improvement in café; (3) data tracking for 1 yr to allow acclimation to new cafeteria offerings; (4) attendance at health/nutrition focused campus events; (5) # of appointments with RDN/health coach (students/employees) | Full-time Registered Dietitian to service all campuses; UR to promote change; food service contract company to support this initiative | June, 2024 | Every 6 months
Develop a centralized website that connects to appropriate University interactive calendars to increase awareness of wellness activities, resources and programs and to facilitate program registration. | Identify internal and external resources to include on the website; develop content and videos, as appropriate | CWO in collaboration with Wellness Advisory Committee; University Relations | (1) Number of clicks on website; (2) length of time spent on site and each link within the site; (3) number of program registrations through the interactive calendar | University Relations to create website in collaboration with Chief Wellness Officer and Wellness Advisory Committee; designated staff to maintain and update the website as needed | December, 2022 | Semi-annually
Leverage social media channels to enhance knowledge and increase awareness of wellness-focused activities, resources, and programs. | Use existing social media channels to engage members of the Pace community (e.g. tik tok, Insta, twitter SetterSync) | University Relations and Chief Wellness Officer staff; student engagement areas; VP for Student Affairs and associate deans for students | (1) Number of clicks on channels; (2) Number of likes/comments | Social media person to establish content and monitor and report on data. | June, 2023 | Quarterly